## Sprint I
Sprint |  | 1 |  | BUS TICKET BOOKING
C1SE-06 Team
# | Hours available per Sprint | Member Name |  | Comments/Notes
1 | 35 | Nguyen Thi Thanh Huong |  | Start Date: 01.Sep.2017 | Start date | 2025-04-05
2 | 42 | Nguyen Pham Anh Huong |  | End Date: 01.Otc. 2017 | End date | 2025-04-17
3 | 29.5 | Le Minh Hieu
4 | 24 | Cao Minh
SUM | 130.5 |  |  | Remanning hours |  | 0 | [21 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [26 empty] | x
[9 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) |  | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 0 05/04/2025 | Day -1 06/04/2025 | Day -2 07/04/2025 | Day -3 08/04/2025 | Day -4 09/04/2025 | Day -5 10/04/2025 | Day -6 11/04/2025 | Day -7 12/04/2025 | Day -8 13/04/2025 | Day -9 14/04/2025 | Day -10 15/04/2025 | Day -11 16/04/2025 | Day -12 17/04/2025 | Thanh Huong | Anh Huong | Hieu | Minh
[7 empty] | 130.5 | 0 | 131 | 120 | 93 | 87 | 77 | 59 | 42 | 35 | 31 | 20 | 15 | 14 | 14
1 | Sprint Detail Plan |  |  |  | All member | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
2 | Sprint Backlog |  |  |  | All member | Completed | 4 | 0 | 4 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
3 | Pre-sprint:fan xxzt | Project Proposal |  |  | All member | Completed | 4 | 0 | 4 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
4 |  | DESCRIPTION OF PROJECT REQUIREMENTS FORM |  |  | All member | Completed | 4 | 0 | 4 | 4 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
5 | Data Modeling | Designing Database |  |  | Thanh Huong | Completed | 5 | 0 | 5 | 5 | 5 | 5 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | x |  |  |  | 5
6 |  | Designing ERD |  |  | Thanh Huong | Completed | 5 | 0 | 5 | 4 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 5
7 |  | Designing the Fact Tables |  |  | Thanh Huong | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | x |  |  |  | 3
8 |  | Designing Mapping Data |  |  | Thanh Huong | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 3
9 | Database/ Physical Design | Configuring Databases |  |  | Hieu | Completed | 4 | 0 | 4 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 4
10 |  | Creating Database Structure |  |  | Hieu | Completed | 4 | 0 | 4 | 4 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | x |  | 4
11 |  | Creating the Normalized Data Store |  |  | Thanh Huong | Completed | 4 | 0 | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | x |  |  |  | 4
12 |  | Summary Tables |  |  | Minh | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 3
13 | Set up database | Create database tables queries |  |  | Hieu | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  |  | x |  | 4
14 |  | Run database queries |  |  | Hieu | Completed | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | x |  | 3
15 | Design | Prototype |  |  | Cao Minh | Completed | 6 | 0 | 6 | 6 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 6
16 |  | Homepage UI |  |  | Anh Huong | Completed | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 |  | x |  |  | 5
17 |  | AdminPage UI |  |  | Anh Huong | Completed | 5 | 0 | 5 | 5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 |  | x |  |  | 5
18 | Build UI | Implement basic components | Conference Detail API |  | Anh Huong | Completed | 6 | 0 | 6 | 6 | 6 | 6 | 5 | 5 | 3 | 3 | 3 | 3 | 2 | 2 | 2 |  | x |  |  | 6
19 |  | InfoSection component | Conferences List & Switch Conference API |  | Anh Huong, Hieu | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | x | x |  | 2
20 |  | Navbar in Homepage UI |  |  | Hieu | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 |  |  | x |  | 4
21 |  | Footer UI |  |  | Hieu | Completed | 2 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 2
22 |  | Homepage UI |  |  | Anh Huong | Completed | 5 | 0 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 |  | x |  |  | 5
23 |  | Admin page UI |  |  | Anh Huong | Completed | 5 | 0 | 5 | 5 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 5
24 |  | Contact page UI |  |  | Anh Huong | Completed | 3 | 0 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 3
25 |  | Navbar in Admin GUI |  |  | Hieu | Completed | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 3
26 |  | Toolbar GUI |  |  | Minh | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 3
27 |  | Output log UI |  |  | Minh | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 4
28 | Testing | InfoSection test |  |  | Hieu, Minh | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | x | x | 1
29 |  | Navbar test |  |  | Minh | Completed | 1.5 | 0 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | x | 1.5
30 |  | Footer test |  |  | Minh | Completed | 2 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | x | 2
31 |  | Homepage test |  |  | Minh | Completed | 5 | 0 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 |  |  |  | x | 5
32 |  | Admin page test |  |  | Hieu | Completed | 5 | 0 | 5 | 5 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  |  | x |  | 5
33 |  | Contact page test |  |  | Hieu | Completed | 2 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 2
34 |  | Toolbar test |  |  | Hieu | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  |  | x |  | 4
[5 empty] | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[5 empty] | 9.6 |  |  | EST | 130.5 | 120.9 | 111.3 | 101.7 | 92.1 | 82.5 | 72.9 | 63.3 | 53.7 | 44.1 | 34.5 | 24.9 | 15.3
[8 empty] | Actual | 131 | 120 | 93 | 87 | 77 | 59 | 42 | 35 | 31 | 20 | 15 | 14 | 14
Note on C1: Change this to sprint number.
Note on A12: Change if task is from prior sprint.
Note on B12: Enter backlog ID here.
Note on C12: Break down user story into detailed tasks (Tests, Integration, Research, etc.)
Note on F12: Enter name of team member(s) who originated the task.
Note on G12: Enter name(s) of team members assigned to the task.
Note on I12: Enter initial estimate here.
Note on J12: Completed. DO NOT EDIT this column. It is based on column 14 and used by product backlog for velocity.

## Sprint II
Sprint |  | 2 | BUS TICKET BOOKING
C1SE-06 Team
# | Hours available per Sprint | Member Name | Comments/Notes
1 | 17.1667 | Nguyen Thi Thanh Huong | Start Date: 01.Sep.2017 | Start date | 2025-04-18
2 | 20.6667 | Nguyen Pham Anh Huong | End Date: 01.Otc. 2017 | End date | 2025-04-30
3 | 21.6667 | Le Minh Hieu
4 | 22.8333 | Cao Minh
SUM | 82.3333 |  | Remanning hours |  | 1.3333 | [21 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [25 empty] | x
[8 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 0 18/04/2025 | Day -1 19/04/2025 | Day -2 20/04/2025 | Day -3 21/04/2025 | Day -4 22/04/2025 | Day -5 23/04/2025 | Day -6 24/04/2025 | Day -7 25/04/2025 | Day -8 26/04/2025 | Day -9 27/04/2025 | Day -10 28/04/2025 | Day -11 29/04/2025 | Day -12 30/04/2025 | Thanh Huong | Anh Huong | Hieu | Minh
[6 empty] | 81 | 0 | 81 | 77 | 54 | 47 | 39 | 34 | 26 | 22 | 16 | 16 | 12 | 9 | 9
1 | Sprint Detail Plan |  |  | All member | Completed | 4 | 0 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | x | x | x | x | 1
2 | Sprint Backlog |  |  | All member | Completed | 4 | 0 | 4 | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | x | x | x | x | 1
3 | Pre-sprint | Planning meeting |  | All member | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1.3333
4 |  | Sprint Retrospective |  | Tung, Loc, Hieu | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | x | x | x | 1.3333
5 | Entity/Repository Layer | Create entity match table in database |  | Thanh Huong | Completed | 4 | 0 | 4 | 4 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 4
6 |  | Create repository |  | Thanh Huong | Completed | 6 | 0 | 6 | 6 | 5 | 5 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 0 | 0 | x |  |  | x | 3
7 |  | Correctly map relationship between tabls |  | Thanh Huong | Completed | 4 | 0 | 4 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 4
8 | Design form CRUD User/Admin | Designing CRUD form for user |  | Anh Huong | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | x |  |  | 3
9 |  | Validate form and handle errors |  | Anh Huong, Hieu | Completed | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 |  | x | x |  | 1.5
10 |  | Designing CRUD form for admin |  | Anh Huong | Completed | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 |  | x |  |  | 3
11 |  | Optimize responsive layout |  | Anh Huong | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 |  | x |  |  | 4
12 |  | Call API and connect data to UI |  | Anh Huong,Hieu,Minh | Completed | 3 | 0 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | x | x | x |  | 1
13 |  | Validating extract process |  | Hieu | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 4
14 | CRUD API | Write API CRUD for entity |  | Thanh Huong | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 3
15 |  | Write API booking and send sms |  | Thanh Huong | Completed | 6 | 0 | 6 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | x |  |  | x | 3
16 |  | Write test case |  | Thanh Huong | Completed | 3 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  | x | 1.5
17 |  | Testing with Postman |  | Thanh Huong | Completed | 3 | 0 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | x | x | 1.5
18 | Testing | Testing layout list item Trip |  | Minh, Hieu | Completed | 3 | 0 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x | x | 1.5
19 |  | Testing booking and payment on UI User |  | Minh, Hieu | Completed | 4 | 0 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 |  |  | x | x | 2
20 |  | Testing layout manage on UI Admin |  | Minh, Hieu | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  |  | x | x | 1.5
21 |  | Testing Login/ Logout |  | Minh, Hieu | Completed | 3 | 0 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x | x | 1.5
22 |  | Testing role with login |  | Minh, Hieu | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | x | x | 1.5
|  |  |  | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  |  | 6.5 |  |  | EST | 81 | 74.5 | 68 | 61.5 | 55 | 48.5 | 42 | 35.5 | 29 | 22.5 | 16 | 9.5 | 3
[7 empty] | Actual | 81 | 77 | 54 | 47 | 39 | 34 | 26 | 22 | 16 | 16 | 12 | 9 | 9
Note on C1: Change this to sprint number.
Note on A12: Change if task is from prior sprint.
Note on B12: Enter backlog ID here.
Note on C12: Break down user story into detailed tasks (Tests, Integration, Research, etc.)
Note on F12: Enter name of team member(s) who originated the task.
Note on G12: Enter name(s) of team members assigned to the task.
Note on I12: Enter initial estimate here.
Note on J12: Completed. DO NOT EDIT this column. It is based on column 14 and used by product backlog for velocity.

## Sprint III
Sprint |  | 3 | BUS TICKET BOOKING
C1SE-06 Team
# | Hours available per Sprint | Member Name | Comments/Notes
1 | 12 | Nguyen Thi Thanh Huong | Start Date: 01.Sep.2017 | Start date | 2025-05-01
2 | 26 | Nguyen Pham Anh Huong | End Date: 01.Otc. 2017 | End date | 2025-05-12
3 | 20.5 | Le Minh Hieu
4 | 9.5 | Cao Minh
SUM | 68 |  | Remanning hours |  | 0 | [20 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [24 empty] | x
[8 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 0 01/05/2025 | Day -1 02/05/2025 | Day -2 03/05/2025 | Day -3 04/05/2025 | Day -4 05/05/2025 | Day -5 06/05/2025 | Day -6 07/05/2025 | Day -7 08/05/2025 | Day -8 09/05/2025 | Day -9 10/05/2025 | Day -10 11/05/2025 | Day -11 12/05/2025 | Thanh Huong | Anh Huong | Hieu | Minh
[6 empty] | 68 | 0 | 68 | 57 | 53 | 41 | 34 | 26 | 25 | 16 | 12 | 8 | 4 | 4
1 | Sprint Detail Plan |  |  | All members | Completed | 4 | 0 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | x | x | x | x | 1
2 | Sprint Backlog |  |  | All members | Completed | 4 | 0 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | x | x | x | x | 1
3 | Pre-sprint | Planning meeting |  | All members | Completed | 4 | 0 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | x | x | x | x | 1
4 |  | Sprint Retrospective |  | All members | Completed | 4 | 0 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | x | x | x | x | 1
5 | Backend API Authorize role endpoint with token | Generate JWT Token |  | Thanh Huong | Completed | 3 | 0 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | x |  |  | x | 1.5
6 |  | Create middleware to validate token |  | Thanh Huong, Minh | Completed | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 2
7 |  | Configure role-based access control |  | Thanh Huong | Completed | 2 | 0 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | x |  |  |  | 2
8 | Update front end | Refactor frontend project structure matching backend |  | Hieu, Minh | Completed | 5 | 0 | 5 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 |  |  | x | x | 2.5
9 |  | Update logic fetch API admin/user |  | Hieu, Minh | Completed | 5 | 0 | 5 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x | x | 2.5
10 | Apply token to using API in front end | Store token after login |  | Anh Huong | Completed | 4 | 0 | 4 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | x |  |  | 4
11 |  | Handle expired or invalid token |  | Anh Huong | Completed | 4 | 0 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  | x |  |  | 4
12 |  | Check role from token |  | Hieu | Completed | 5 | 0 | 5 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 5
13 | Handling and display error on front end | Update error message form |  | Hieu | Completed | 5 | 0 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 5
14 |  | Handle form validation errors |  | Hieu | Completed | 4 | 0 | 4 | 4 | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | x |  | 4
15 |  | Testing front end on new change |  | Minh | Completed | 3 | 0 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  |  |  | x | 3
16 | Debug functional | Debug backend for handle more exception |  | Minh | Completed | 3 | 0 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 |  |  |  | x | 3
17 |  | Debug interface |  | Minh | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 |  |  |  | x | 4
18 |  | Retesting all endpoint when changed |  | Hieu | Completed | 3 | 0 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | x |  | 3
|  |  |  | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  |  |  | 6 |  |  | EST | 68 | 62 | 56 | 50 | 44 | 38 | 32 | 26 | 20 | 14 | 8 | 2
[7 empty] | Actual | 68 | 57 | 53 | 41 | 34 | 26 | 25 | 16 | 12 | 8 | 4 | 4
Note on C1: Change this to sprint number.
Note on A12: Change if task is from prior sprint.
Note on B12: Enter backlog ID here.
Note on C12: Break down user story into detailed tasks (Tests, Integration, Research, etc.)
Note on F12: Enter name of team member(s) who originated the task.
Note on G12: Enter name(s) of team members assigned to the task.
Note on I12: Enter initial estimate here.
Note on J12: Completed. DO NOT EDIT this column. It is based on column 14 and used by product backlog for velocity.

## Sprint IV
Sprint |  | 4 | Airline Reversation System
ARS Team
# | Hours available per Sprint | Member Name | Comments/Notes
1 | 88.5 | Nguyen Thi Thanh Huong | Start Date: 01.Sep.2017 | Start date | 2025-05-13
2 | 93.5 | Nguyen Pham Anh Huong | End Date: 01.Otc. 2017 | End date | 2025-05-17
3 | 65.5 | Le Minh Hieu
4 | 53.5 | Cao Minh
SUM | 301 |  | Remanning hours |  | 0 | [13 empty] | x
How to use this: NEW SPRINT 1) Make a copy of this sheet, change X in cell D1 to sprint number. 2) Each team member estimates the number of hours they have to work in the sprint. ENTERING A NEW TASK 1) For the sprint, select a user story from the product backlog (based on input from Product Owner). 2) Break down the user story into tasks of around 0 to 8 hours. 3) For each task, enter the backlog ID in column B. a description of the task, the originator and responsible team members. 4) Finally, and most Important, enter the initial estimate in hours in column H. UPDATING Every day you should re-estimate the tasks entering the new estimate on the next day. This means you could end up with more hours on a task the next day even if you spent time on it in the current day. What is important is to know how much work is left to do. Not how much work was done. | [17 empty] | x
[8 empty] | 0 | 1 | 2 | 3 | 4
No. | BACKLOG ID | Task Description (User Story/Use Case Broken Down) | Originator | Responsible | Status(Not Started In Progress Completed) | Inital Est. | Comp. | Day 0 13/05/2025 | Day -1 14/05/2025 | Day -2 15/05/2025 | Day -3 16/05/2025 | Day -4 17/05/2025 | Thanh Huong | Anh Huong | Hieu | Minh
[6 empty] | 301 | 0 | 301 | 278 | 259 | 234 | 222
1 | Sprint Detail Plan |  |  | All members | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | x | x | x | x | 1
2 | Sprint Backlog |  |  | All members | Completed | 4 | 0 | 4 | 1 | 1 | 1 | 1 | z | x | x | x | 1.3333
3 | Pre-sprint | Planning meeting |  | All members | Completed | 4 | 0 | 4 | 4 | 0 | 0 | 0 | x | x | x | x | 1
4 |  | Sprint Retrospective |  | All members | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | x | x | x | x | 1
5 | Documents | Reworking Proposal |  | Thanh Huong | Completed | 4 | 0 | 4 | 2 | 1 | 1 | 0 | x |  |  |  | 4
6 |  | Reworking Project Plan |  | All members | Completed | 4 | 0 | 4 | 2 | 1 | 1 | 0 | x | x | x | x | 1
7 |  | Architecture Document |  | All members | Completed | 6 | 0 | 6 | 5 | 3 | 3 | 1 | x | x | x | x | 1.5
8 |  | Interface Desgin |  | Anh Huong | Completed | 8 | 0 | 8 | 6 | 6 | 3 | 3 |  | x |  |  | 8
9 |  | Database Design |  | Thanh Huong | Completed | 8 | 0 | 8 | 5 | 5 | 3 | 1 | x |  |  |  | 8
10 |  | Test Plan |  | All members | Completed | 4 | 0 | 4 | 4 | 4 | 0 | 0 | x | x | x | x | 1
11 |  | Test Case |  | All members | Completed | 8 | 0 | 8 | 8 | 8 | 6 | 6 | x | x | x | x | 2
12 |  | Acceptance Criteria |  | Thanh Huong Minh | In Progress | 4 | 0 | 4 | 4 | 4 | 4 | 4 |  | x |  | x | 2
13 |  | Technologies Stack |  | All members | In Progress | 4 | 0 | 4 | 3 | 0 | 0 | 0 | x | x | x | x | 1
14 |  | Team Reflection |  | All members | In Progress | 4 | 0 | 4 | 4 | 4 | 4 | 4 | x | x | x | x | 1
15 |  | Team meeting document |  | Hieu | In Progress | 4 | 0 | 4 | 4 | 3 | 3 | 3 |  |  | x |  | 4
16 |  | Mentor meeting document |  | Hieu | In Progress | 4 | 0 | 4 | 4 | 3 | 3 | 3 |  |  | x |  | 4
17 | Integration payment | Configuration zalo pay |  | Thanh Huong, Minh | In Progress | 12 | 0 | 12 | 12 | 12 | 12 | 12 | x |  |  | x | 6
18 |  | Process logic validation payment |  | Thanh Huong,Anh Huong | Not Started | 12 | 0 | 12 | 12 | 12 | 12 | 12 | x | x |  |  | 6
19 |  | Integration in front end |  | Anh Huong, Hieu | Not Started | 14 | 0 | 14 | 14 | 14 | 14 | 14 |  | x | x |  | 7
20 |  | Testing function payment |  | Anh Huong, Hieu | Not Started | 12 | 0 | 12 | 12 | 12 | 12 | 12 |  | x | x |  | 6
21 | Presentation preparation | Create slide |  | Minh | Completed | 20 | 0 | 20 | 20 | 20 | 20 | 20 |  |  |  | x | 20
22 |  | Make video teching |  | Minh | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 |  |  |  | x | 12
23 | Traning using | Create document tech using |  | Anh Huong | Completed | 10 | 0 | 10 | 8 | 4 | 0 | 0 |  | x |  |  | 10
24 |  | Sevey and collection feedback |  | Anh Huong | Completed | 10 | 0 | 10 | 10 | 8 | 2 | 0 |  | x |  |  | 10
25 | Deployment & Release | Prepare enviroment |  | Minh | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 |  |  | x |  | 12
26 |  | Prepare domain |  | Thanh Huong | Completed | 12 | 0 | 12 | 12 | 12 | 12 | 12 | x |  |  |  | 12
27 |  | Prepare server |  | Hieu | Completed | 35 | 0 | 35 | 35 | 35 | 35 | 35 |  |  | x |  | 35
28 | Final testing | Test all fucntion end to end |  | Hieu, Minh | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 |  |  | x | x | 2
29 |  | Test middleware |  | Hieu | Completed | 4 | 0 | 4 | 4 | 4 | 4 | 4 |  |  | x |  | 4
30 |  | Test UX/UI |  | Anh Huong, Hieu, Minh | Completed | 2 | 0 | 2 | 2 | 2 | 2 | 2 |  | x | x | x | 0.66667
31 |  | Test Database |  | Thanh Huong | In Progress | 8 | 0 | 8 | 8 | 8 | 8 | 8 | x |  |  | x | 4
32 |  | Test Performance |  | Hieu | Completed | 8 | 0 | 8 | 8 | 8 | 8 | 8 |  | x | x |  | 4
33 |  | Integration testing |  | Minh | In Progress | 8 | 0 | 8 | 8 | 8 | 8 | 8 |  | x |  | x | 4
34 | Presentation |  |  | All members | In Progress | 12 | 0 | 12 | 12 | 12 | 8 | 4 | x | x | x | x | 3
35 | Print Document |  |  | Anh Huong | In Progress | 4 | 0 | 4 | 4 | 4 | 4 | 4 |  | x |  |  | 4
36 | Deployment & Release |  |  | Anh Huong | In Progress | 12 | 0 | 12 | 12 | 12 | 12 | 12 |  | x |  |  | 12
|  |  |  | Working hours per day |  |  | Day | 0 | 1 | 2 | 3 | 4
|  |  |  | 10 |  |  | EST | 301 | 291 | 281 | 271 | 261
[7 empty] | Actual | 301 | 278 | 259 | 234 | 222
Note on C1: Change this to sprint number.
Note on A12: Change if task is from prior sprint.
Note on B12: Enter backlog ID here.
Note on C12: Break down user story into detailed tasks (Tests, Integration, Research, etc.)
Note on F12: Enter name of team member(s) who originated the task.
Note on G12: Enter name(s) of team members assigned to the task.
Note on I12: Enter initial estimate here.
Note on J12: Completed. DO NOT EDIT this column. It is based on column 14 and used by product backlog for velocity.

## Note
There are problem with this task, like OT…
By this time this task must be done on plan
Place to input data